## Slide 1: Studio Niva on OmniFlow
×
Project plan: requirements, what OmniFlow covers, what we will build, and the timeline
October 2026 · Prepared by OmniQ Consulting for Studio Niva
Notes: Purpose: agree the scope and plan for moving Studio Niva's operations from five Google Sheets onto OmniFlow.

## Slide 2: Today, Studio Niva runs on five separate Google Sheets
Project Progress
47
sites tracked across 21 construction stages
Project Master
47
projects registered with client and team
Delegation Sheet
1,854
tasks delegated since Nov 2025
Employee Forms
494
leave, conveyance and other requests
Client Master
18
client contacts with birthdays and anniversaries
What gets lost between the sheets
The same project has a different ID or name in different sheets
Site stages show a status but no dates, so delays are invisible
Tasks are not linked to a project, and completed work is rarely checked
Conveyance claims and client feedback are captured but almost never closed
Notes: Numbers are taken from the sheets shared in October 2026.

## Slide 3: What Studio Niva needs from the new system
One project register
Every project with one ID, client, team, scope, documents and MOMs
Live site progress
21 stages per site running in parallel, with planned vs actual dates
Delegation and scorecard
Tasks linked to projects, reminders, red / yellow / green weekly scorecard
Work that is checked
Mentor or reviewer signs off completed tasks and drawings
Leave and HR requests
Apply, approve, substitute buddy, linked to attendance
Conveyance claims
Submit with bill photo, approve, and track what is reimbursed
Client care
Birthday and anniversary reminders, feedback at handover
One view, on the phone
Owner dashboard, mobile app and WhatsApp alerts for everyone

## Slide 4: Seven of twelve needs are already in OmniFlow today
What Studio Niva needs | Where it lives in OmniFlow | Status
Task delegation, reminders and WhatsApp alerts | Delegation and My Tasks | Ready
Checking and signing off completed work | Evidence and sign-off on tasks | Ready
Step-by-step processes (change requests, approvals) | FMS process flows | Ready
General requests to the office | Help requests | Ready
Mobile app and notifications | OmniFlow mobile app | Ready
Leave applications and approvals | Leave and Attendance | Configure
Client and family contacts | Customers and contacts | Configure
One project register | Projects | New
Site progress with parallel stages | Milestone Tracker | New
Revision-based weekly R / Y / G score | Weekly Scorecard | New
Conveyance claims with approval and payout | Claims approval | New
Birthday, anniversary reminders and feedback | Client Care | New
5
Ready
work from day one
2
Configure
set up to Studio Niva's rules
5
New
built as OmniFlow features
Notes: Ready = available as is. Configure = available, needs Studio Niva's settings. New = will be built as an OmniFlow feature and switched on for Studio Niva.

## Slide 5: Five additions close every gap, built into OmniFlow
Projects
One record per project with a single ID
Client, mentor, architect, designer, supervisor
Scope, site address, documents and MOMs
Every task and flow linked to its project
Milestone Tracker
21 stages from Studio Niva's own list
Done, Ongoing, Upcoming, NA, On Hold
Planned vs actual dates, late flags
All sites on one board
Scorecard
Counts each change of due date
Second change moves the task a week
Weekly red / yellow / green per person
Next week's target mix vs actual
Claims approval
Conveyance with photo of the bill
Approve or reject in one tap
Monthly total per person
Paid status recorded
Client Care
Family members under each client
Birthday and anniversary reminders
Feedback form at handover
Score per project
Projects and Milestone Tracker come first: everything else links to them.
Notes: Each addition becomes a standard OmniFlow feature switched on for Studio Niva, so it keeps improving with every release.

## Slide 6: A real project, end to end
Residence at F-86, Ashok Vihar: Studio Niva's busiest site, with 155 tasks delegated so far

## Slide 7: Milestone Tracker: the whole site on one screen
01
Site Survey
Done
02
Foundation
Not needed
03
Plinth Beam
Not needed
04
DPC Waterproofing
Not needed
05
Stilt Brickwork
Not needed
06
Sewerage
Not needed
07
Slab Casting
Not needed
08
Brickwork / Rangat
Not needed
09
Wall Plumbing
Done
10
Wall Electrical
Done
11
AC Routing
Done
12
Pipe Route Records
Done
13
Plaster
Done
14
PCC and Levels
Done
15
False Ceiling
Done
16
Marble / Tile Laying
Ongoing
17
Waste Tiling
Done
18
Stone / Tile Work
Ongoing
19
Woodwork
Ongoing
20
Finishes
Upcoming
21
Furniture Marking
Not needed
Done: 9 stages
Ongoing: 3 stages
Upcoming: 1 stage
Not needed: 8 stages
Three stages run at the same time. Marble, stone work and woodwork move in parallel, so the tracker shows each stage side by side instead of forcing one order.
PROJECT 140
Residence at F-86, Ashok Vihar
Mentor
Arushi
Architect
Ritika
Designer
Kasvi
Site supervisor
Arvind
Scope
Architecture + Interiors
9 of 13
applicable stages done
Notes: Stage statuses are F-86's real statuses from the progress sheet. Dates shown are illustrative until Studio Niva confirms planned dates.

## Slide 8: FMS runs the step-by-step work inside a stage
Client change request
F-86 had MBR, son's bedroom and double-height changes
Client asks for a change
Mentor
Designer revises drawing
Kasvi
Mentor review
Arushi
Client approves
Client
Issued to site
Arvind
Woodwork execution
Runs while the Woodwork stage is Ongoing
Shop drawings
Designer
Client sign-off
Client
Order with carpenter
Office
Installation
Site supervisor
Snag check
Mentor
Each step has an owner, a target time and a reminder; nothing waits on a phone call.
Notes: Both flows are examples built from real F-86 tasks in the delegation sheet (MBR changes, double-height changes, woodwork). Owners and target times are suggestions for Studio Niva to confirm.

## Slide 9: How the pieces work together on F-86
1. Milestone Tracker
Woodwork moves to Ongoing on F-86
2. FMS flow starts
Woodwork execution flow opens automatically with its five steps
3. Tasks to people
Each step creates a task with a due date, reminder and WhatsApp alert
4. Checked and closed
Mentor signs off; the scorecard records on time or revised
5. Stage marked Done
When the flow finishes, Woodwork turns Done on the tracker
Owner dashboard
All sites, late stages, open approvals and this week's scorecard
Notes: Milestone Tracker gives the site picture, FMS runs the process inside a stage, Delegation handles day-to-day tasks, and the dashboard and scorecard read from all three.

## Slide 10: What each person sees in OmniFlow
Principal / Owner
All sites on one board
Late stages and red tasks flagged
Weekly scorecard per person
Mentor
Their projects and stages
Drawings waiting for review
Signs off completed work
Architect / Designer
My Tasks, linked to each project
Change requests assigned to them
Due-date changes need a reason
Site supervisor
Updates stages from site on mobile
Conveyance claim with bill photo
Issued drawings for the site
Office admin
Leave and claim approvals
Client birthday reminders
New project set-up in minutes
Everyone uses the same OmniFlow app on web and phone; each person sees only what their role needs.

## Slide 11: Full go-live in ten weeks, with the first modules live by 30 October
W1
5 Oct
W2
12 Oct
W3
19 Oct
W4
26 Oct
W5
2 Nov
W6
9 Nov
W7
16 Nov
W8
23 Nov
W9
30 Nov
W10
7 Dec
Kick-off and data clean-up
Fix project IDs, collect stage dates, users
Go-live: ready modules
Delegation, leave, requests, contacts, mobile
Build: Projects + Milestone Tracker
Register, 21-stage board, F-86 pilot
Build: Scorecard, Claims, Client Care
Weekly R / Y / G, conveyance approval, reminders
Parallel run and training
Sheets and OmniFlow side by side, then retire sheets
Key dates
30 Oct
First modules live
20 Nov
Milestone Tracker live
11 Dec
Full go-live
Notes: Proposed timeline from a 5 October 2026 start. It assumes plan sign-off this week and allows a buffer for Diwali week in early November.

## Slide 12: What we need from Studio Niva to start
1
Confirm project IDs
IDs 150 and 151 differ between sheets; add projects 152 to 167 to the tracker
2
Share planned stage dates
Planned start and finish for each active site, so delays show from day one
3
Agree the scoring rule
Keep the score on due-date changes only, or also count late completion
4
Set claim approvals
Who approves conveyance, and whether it is paid with salary or separately
5
Name a project champion
One person at Studio Niva for set-up questions, testing and training
THIS WEEK
Studio Niva signs off this plan
OmniFlow workspace set up with the team list
Kick-off session with mentors and admin
Data clean-up of projects and clients begins

## Slide 13: One place for every site and task
×
Thank you. Questions and changes to this plan are welcome.
OmniQ Consulting · omniqconsulting.com